## General Schedule
Task | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Design Frame | bar: Oct
Order Parts for Frame | bar: Oct
Build Frame | bar: Oct
Design Hardware | bar: Oct to Dec
Order Hardware | bar: Oct to Dec
Assemble Hardware | bar: Nov to Dec
Develop Motor Software | bar: Dec to Feb
Develop Tracking Software | bar: Jan to Mar
Develop Networking Capabilities | bar: Feb to Mar
Motor Testing | bar: Apr to Jun
Motor Control Testing | bar: Apr to Jun
Tracking Testing | bar: Apr to Jun
Stretch Goals (If ahead of schedule)
Documentation
Engineer | Oct: 15 hrs. /week * 10 weeks = 150 hrs. @ $50 / hr.; Nov: 7500
Part Cost | Nov: 495.67
Total: | Nov: 7995.67

## Costs
Part | Link | Date Purchased | Price | Qty | Cost
Raspberry Pi | https://thepihut.com/products/raspberry-pi-3-model-b?src=raspberrypi | N/A (Already Owned) | 0 | 1 | 0
Nema 17 Stepper Motor | https://www.omc-stepperonline.com/nema-17-stepper-motor-l-40mm-gear-ratio-100-1-plm-series-planetary-gearbox-17hs15-1584s-plmg100 | 2022-10-28 | 37.16 | 2 | 74.32
DM542T Digital Stepper Driver | https://www.omc-stepperonline.com/digital-stepper-driver-1-0-4-2a-20-50vdc-for-nema-17-23-24-stepper-motor-dm542t | 2022-10-28 | 20.99 | 2 | 41.98
Power Supply | https://www.amazon.com/dp/B08GFQZFC1?ref=ppx_yo2ov_dt_b_product_details&th=1 | 2022-11-28 | 39.99 | 1 | 39.99
Timing Belt | https://www.amazon.com/dp/B07JKT5BZQ?psc=1&ref=ppx_yo2ov_dt_b_product_details | 2023-02-05 | 14.99 | 1 | 14.99
8mm Shaft | https://www.amazon.com/dp/B01B27MJC6?psc=1&ref=ppx_yo2ov_dt_b_product_details | 2023-02-05 | 7.99 | 1 | 7.99
8mm Bearings | https://www.amazon.com/dp/B07TNNX9YX?psc=1&ref=ppx_yo2ov_dt_b_product_details | 2023-02-05 | 6.99 | 1 | 6.99
5mm to 8mm Coupling | https://www.amazon.com/dp/B07RMZCLZ3?psc=1&ref=ppx_yo2ov_dt_b_product_details | 2023-02-05 | 12.99 | 1 | 12.99
3.3V to 5V Level Shifter | https://www.amazon.com/dp/B06XWVZHZJ?psc=1&ref=ppx_yo2ov_dt_b_product_details | 2023-02-05 | 8.99 | 1 | 8.99
Dobsonian Base |  |  | 134.3 | 1 | 134.3
Tube Assembly |  |  | 67.95 | 1 | 67.95
Paint and Sandpaper |  |  | 48.96 | 1 | 48.96
Misc hardware (Bearings, Legs, Levels) |  |  | 61.76 | 1 | 61.76
Shipping |  |  | 26.41 | 1 | 26.41
|  |  |  | Total | 547.62
8047.62

## Fall 2022 Schedule
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Restore used telecope parts | bar: Week 1 to Week 2
Design bracket for vertical axis | bar: Week 2
Build bracket for vertical axis | bar: Week 2 to Week 3
Design base for horizontal axis | bar: Week 3
Build bracket for horizontal axis | bar: Week 3 to Week 4
Assemble functional non motorized telescope | bar: Week 5
Research motor types | bar: Week 1 to Week 3
Research processors / boards | bar: Week 3 to Week 4
Research hardware for network requirement | bar: Week 3 to Week 4
Decide motor type | bar: Week 4
Decide processor | bar: Week 4
Order motors | bar: Week 5
Order processor / board | bar: Week 5
Order power supply / peripherals | bar: Week 5 to Week 6
Design motor housing / gearing | bar: Week 6 to Week 9
Design board housing | bar: Week 6 to Week 9
Familiarize with processor / board | bar: Week 7 to Week 10
Familiarize with controlling motors | bar: Week 7 to Week 12
Stretch Goals (If ahead of schedule) | bar: Week 4 to Week 5; Week 11 to Week 12
Documentation

## Winter 2023 Schedule
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Legend:
1. Finish non-motorized telescope assembly. | [11 empty] | Complete | bar: Week 1 to Week 3
a) Drill holes into turntable and assemble uprights. | bar: Week 1 to Week 3
b) Drill holes and screw in horizontal struct piece. | bar: Week 1 to Week 3
c) Paint unfinished pieces | [11 empty] | In progress | bar: Week 4 to Week 5
2. Create gearing system. | bar: Week 4 to Week 5
a) Design and print large pulley gear. | bar: Week 4 to Week 5
b) Order smaller gear and timing belts. | [11 empty] | Not Started | bar: Week 4 to Week 5
3. Connect power adapter to power supply. | bar: Week 4 to Week 6
4. Connect power supply to stepper drivers. | bar: Week 4 to Week 6
5. Connect level shifter for the 3.3V I/O of Raspberry Pi to 5V of the stepper motor driver. | bar: Week 4 to Week 6
6. Develop software to drive motors. | bar: Week 4 to Week 7
a) Develop software to drive 2 motors at once. | bar: Week 5 to Week 7
7. Develop software to aim telescope. | bar: Week 6 to Week 11
a) Find the math behind aiming 2 axis control in 3D geometric space. | bar: Week 6 to Week 11
b) Apply the math to the code for driving the motors. | bar: Week 8 to Week 11
8. Develop software to track a coordinate as the earth rotates. | bar: Week 8 to Week 11
a) Develop software for calculating sidereal time. | bar: Week 8 to Week 11
9. Create or purchase board and electronic housing. | bar: Week 4 to Week 11

## Spring 2023 Schedule
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Legend:
Remake breadboard circuit on soldered board | [11 empty] | Complete | bar: Week 1 to Week 2
Rewire all connections inside waterproof box | bar: Week 1 to Week 3
Finalize motor control | bar: Week 2 to Week 3
Generate motor testing plan | [11 empty] | In progress | bar: Week 2 to Week 3
Generate control testing plan | bar: Week 2 to Week 3
Generate tracking testing plan | bar: Week 2 to Week 3
Test motors | [11 empty] | Not Started | bar: Week 4 to Week 9
Test control program | bar: Week 4 to Week 9
Test tracking capabilities | bar: Week 4 to Week 9
Record results | bar: Week 4 to Week 11
Compile summary documentation | bar: Week 9 to Week 11
Stretch Goals:
Add a camera
Add GPS Module
Design and print replacement focuser
Find better solution to shaft connection on small gear